## Sheet1
TASK: | Back-end, MongoDB connection, registration and login
Week7
TASKS |  | Expected | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03
1 | Connection Mongodb to VS | 2 | 2
2 | Create Database Tables | 4 | 2 | 2
3 | Create Interface in VS | 4 |  | 2 | 2
4 | Test Register New User | 3 |  |  | 2 | 1
5 | Test User Log In | 2 |  |  |  | 1 | 1
| TOTAL | 15 | 4 | 4 | 4 | 2 | 1
| Remaining | 15 | 11 | 7 | 3 | 1 | 0
| Predicted | 15 | 10 | 5 | 3 | 1 | 0
TASK: | Create User Detail Page and Upload Recipe Function
Week9 and Week 10
TASKS |  | Expected | 2023-11-10 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-20
1 | Modify user information api on the back-end | 5 | 2023-11-10: 4; 2023-11-13: 1
2 | Upload recipe function api on the back-end | 5 | 2023-11-13: 3; 2023-11-14: 2
3 | Recipe data initialization on he back-end | 3 | 2023-11-14: 2; 2023-11-15: 1
4 | Personal information display and modification | 5 | 2023-11-15: 3; 2023-11-16: 2
5 | Like and upload the recipe list component creation | 4 | 2023-11-16: 2; 2023-11-17: 2
6 | Front-end upload recipe page | 5 | 2023-11-17: 3; 2023-11-20: 2
7 | Front-end and back-end data interaction | 3 | 2023-11-20: 3
| TOTAL | 30 | 4 | 4 | 4 | 4 | 4 | 5 | 5
| Remaining | 30 | 26 | 22 | 18 | 14 | 10 | 5 | 0
| Predicted | 30 | 25 | 20 | 15 | 10 | 5 | 2 | 0
TASK: | Design of the Home Page and Recipe Details Interface
The days before
TASKS |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
1 | Project initialization | The days before Day1: 2; The days before Day2: 2
2 | Get recipe details from Themealdb | The days before Day1: 4; The days before Day2: 2; The days before Day3: 2
3 | NavBar Component | The days before Day1: 5; The days before Day3: 1; The days before Day4: 4
4 | Recipe Card Component | The days before Day1: 5; The days before Day4: 3; The days before Day5: 2
5 | Homepage Layout | The days before Day1: 5; The days before Day5: 4; The days before Day6: 1
6 | Create the recipe details component | The days before Day1: 3; The days before Day6: 1; The days before Day7: 2
7 | Layout the recipe details interface | The days before Day1: 5; The days before Day7: 2; The days before Day8: 3
| TOTAL | 29 | 4 | 3 | 7 | 6 | 2 | 4 | 3
| Remaining | 29 | 25 | 22 | 15 | 9 | 7 | 3 | 0
| Predicted | 29 | 24 | 19 | 14 | 9 | 4 | 0 | 0
TASK: | Like Feature Implementation
Semester2-Week2
TASKS |  | Expected | 2024-01-19 | 2024-01-22 | 2023-01-23 | 2024-01-24 | 2024-01-25
1 | Add favourite iconbutton and add styles when clicking | The days before Day1: 4; The days before Day2: 4
2 | Add server favourite api | The days before Day1: 4; The days before Day3: 3; The days before Day4: 1
3 | Add client favourite api | The days before Day1: 4; The days before Day4: 3; The days before Day5: 1
4 | Update the useContext attributes in pages | The days before Day1: 5; The days before Day5: 3; The days before Day6: 2
| TOTAL | 17 | 13 | 10 | 6 | 2 | 0
| Remaining | 17 | 14 | 10 | 6 | 2 | 0
| Predicted | 17 | 12 | 8 | 4 | 1 | 0